## Sheet2
Sum of Story Points | Column Labels
Row Labels | Done | In Progress | To Do | Grand Total
[Access Management] Network Builder Tool Enhancements - FY24Q2 | 3.5 |  | 46.5 | 50
[National Map] Map and Networks timestamp updates | 3.5 | 5 | 3.5 | 12
[National Map] Display Additional Layers |  | 11 | 24 | 35
[National Map] Layers Panel Refactoring/Enhancements - Right side | 2 |  | 15.5 | 17.5
[National Map] NatMap System Performance | 17 | 8 | 26.5 | 51.5
[National Map] Road Selection Tool for NatMap | 3.5 |  | 11.5 | 15
[National Map] Save and Retrieve My Network Views | 12 | 1 | 5 | 18
[National Map] Splash Screens and Legal Requirements | 10 |  |  | 10
[National Map] Steel Thread - Type 1 Road Train Network - Spatial | 7 |  | 3 | 10
[Network Management] Spatial - Network Features | 22 | 3 | 3 | 28
[NUR/Builder/National Map] Enhance display and edit of selected Conditions/Restrictions - NHVR NatMap Road Selection Panel | 8 | 2 | 15.5 | 25.5
[Road Management] Refactoring Road Management and Implementing Workflow Side Strip | 1 |  | 10.5 | 11.5
[Road Management] Support for multiple road ownership scenarios |  |  | 3.5 | 3.5
[Spatial] Tracking and Analytics | 4.5 |  |  | 4.5
FY24 - RP & NGRP - Production Support | 14 | 3 | 80 | 97
Network Builder / NUR / NatMap - Support for Conditions / Restrictions | 32 |  |  | 32
Road Management Production Support | 101.5 |  | 14 | 115.5
Spatial - Tech Debt - FY24Q2 | 31.5 | 3.5 | 28 | 63
Tech Enablement: Automate the provision of non-NHVR data sources for National Map | 5 |  | 37 | 42
Visualise Asset structures within layers on NHVR Maps | 3.5 |  | 7 | 10.5
(blank) | 3.5 |  |  | 3.5
Grand Total | 285 | 36.5 | 334 | 655.5

## Jira (31)
Issue Type | Issue key | Issue id | Parent id | Summary | Status | Custom field (Epic Link) | Epic Link Summary | Story Points | Team Id | Team Name | Custom field (Delivery Period)
Story | NSSP-6261 | 43308 |  | [Network Management] Add a toggle feature for NHVR and RM users to view active NURs on the map layer | To Do | NSSP-6055 | [Access Management] Network Builder Tool Enhancements - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Story | NSSP-6259 | 43306 |  | [Network Management] Show where active Update Requests are located on the viewed map layer | To Do | NSSP-6055 | [Access Management] Network Builder Tool Enhancements - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Story | NSSP-6257 | 43298 |  | [Network Management] Display Active NURs/Consultations Details for NHVR and RM users when viewing a network. | To Do | NSSP-6055 | [Access Management] Network Builder Tool Enhancements - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Story | NSSP-6166 | 43089 |  | Add modal prompt to warn user if they are about to lose a selection (by switching tools). | To Do | NSSP-6055 | [Access Management] Network Builder Tool Enhancements - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-6165 | 43088 |  | Introduce “Shift” key support for Area Select tool across the application | To Do | NSSP-6055 | [Access Management] Network Builder Tool Enhancements - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-6120 | 42967 |  | Enhance Map-Tools Consistency & Functionality | Done | NSSP-6055 | [Access Management] Network Builder Tool Enhancements - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-5912 | 42416 |  | Drawer UI: Resolving conflicted unmanaged/private/othermanager segments from selection | To Do | NSSP-6055 | [Access Management] Network Builder Tool Enhancements - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-5911 | 42415 |  | Map UI: Resolving conflicted unmanaged/private/othermanager segments from selection | To Do | NSSP-6055 | [Access Management] Network Builder Tool Enhancements - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Task | NSSP-5866 | 42296 |  | [UX] Review AOR, starting center and zoom | To Do | NSSP-6055 | [Access Management] Network Builder Tool Enhancements - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-5272 | 40801 |  | [Map Management Tools] Contextual menu: Extend Road Selection | To Do | NSSP-6055 | [Access Management] Network Builder Tool Enhancements - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-10 | CX-Design
Story | NSSP-4546 | 38647 |  | Spike - [Network Management] Test - All URL's need to work in the current Production portal frontend | To Do | NSSP-6055 | [Access Management] Network Builder Tool Enhancements - FY24Q2 | 1 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-3991 | 37868 |  | [Network Management] 'Changed' segment style | To Do | NSSP-6055 | [Access Management] Network Builder Tool Enhancements - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-3810 | 37522 |  | [Network Builder] New - Access list: Fetch and View saved segment groupings | To Do | NSSP-6055 | [Access Management] Network Builder Tool Enhancements - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Enabler | NSSP-3672 | 37336 |  | Backend Enabler: Enhancements to the 'Find Segments by Route/Waypoints' API | To Do | NSSP-6055 | [Access Management] Network Builder Tool Enhancements - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Enabler | NSSP-1429 | 32320 |  | Query / investigation tool "What is the history of this piece of road?" | To Do | NSSP-6055 | [Access Management] Network Builder Tool Enhancements - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-4840 | 39465 |  | Connex Tunnels Height Markers in RP New Layer | Done | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Bug | NSSP-3664 | 37322 |  | HV Route in Route Planner Uses Queenscliff to Sorrento Ferry | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Task | NSSP-3588 | 37197 |  | Handover documentation - Legacy RP HV network generation | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-3532 | 37011 |  | Road Management Area Polygon tool not showing all segments | Done | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Task | NSSP-3484 | 36960 |  | [NGRP] Update instances of dual road ownership within Wellington Shire, Victoria | Done | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Bug | NSSP-3339 | 36653 |  | [NGRP] Route IDs 'inherit' outdated road ownership data | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Enabler | NSSP-3036 | 35912 |  | Powershell script publishes data to ArcGIS Server | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-2700 | 35095 |  | Replace Jurisdictional Border Layers in RP and NGRP with OSM border data | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-2689 | 35059 |  | Migrate State Roads Tasmania to OSM | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-2446 | 34510 |  | [NGRP] Improve routing adherence to the Broken Hill HV bypass, New South Wales | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-2404 | 34435 |  | [NGRP] Improve routing adherence to the Gawler HV bypass, South Australia | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Task | NSSP-2376 | 34334 |  | Add missing Vic LENs to Route Planner Network Layers | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-2304 | 34248 |  | Support ability to prohibit access on roads Under Construction | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-2089 | 33722 |  | [NGRP] Map in Case Details tab in Portal not zooming without the screen splitting and data disappearing | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-1804 | 33208 |  | Clearly display RM Boundaries layer on Satellite and Hybrid map layers | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-1701 | 33031 |  | [NGRP] Investigate routing performance between Gateway Mtwy and Coopers Plains Industrial Estate | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Enabler | NSSP-1686 | 32972 |  | Backend Enabler: Return OSM State/National road names in the routing API response | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Enabler | NSSP-1685 | 32971 |  | DB Enabler: Extract and store OSM State/National road names into the way2go db | In Progress | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Enabler | NSSP-1653 | 32112 |  | [PORTAL-Q1/23] Upgrade dependencies to support NodeJS v16 (LTS) | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-1557 | 32745 |  | [NGRP] Combine Route Summary entries with same road name. | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Enabler | NSSP-1380 | 32243 |  | [NGRP] Super-fast general access routing option | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-1351 | 10394 |  | Zoom issue in RoutePlanner | Done | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Enabler | NSSP-1057 | 10815 |  | Revisit OSM ingestion / merge processes - need to speed things up a bit? | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Enabler | NSSP-1044 | 10486 |  | [SPATIAL-Q4] Defence Route Maps (data refresh) - Rebuild | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-865 | 10397 |  | Toggle Road 'Alt_Name' in Portal Route Summary | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-830 | 10132 |  | [NGRP] Always use State Road Name in Route Summary | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-820 | 10129 |  | Provide Date Routable and visual map data were last updated | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Task | NSSP-763 | 10793 |  | [SPATIAL-Q4] Review "oneway=-1" data from OSM | To Do | NSSP-5641 | FY24 - RP & NGRP - Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-6311 | 43474 |  | [NatMap] Display Features (points and polygons) in National Maps | In Progress | NSSP-5892 | [National Map] Display Additional Layers | 8 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-6195 | 43190 |  | [National Map] Use our National Map layers (which differ from Network Management layers) to display networks | In Progress | NSSP-5892 | [National Map] Display Additional Layers | 3 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Story | NSSP-5909 | 42413 |  | [National Map] Present and apply base map view options | To Do | NSSP-5892 | [National Map] Display Additional Layers | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Story | NSSP-5908 | 42409 |  | [National Map] Clear my selected layers on my NatMap view | To Do | NSSP-5892 | [National Map] Display Additional Layers | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Story | NSSP-5907 | 42408 |  | [National Map] Present my selected layers on my NatMap view | To Do | NSSP-5892 | [National Map] Display Additional Layers | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Story | NSSP-5905 | 42405 |  | [National Map] Show my selected layers in the “Layer panel” | To Do | NSSP-5892 | [National Map] Display Additional Layers | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Task | NSSP-5833 | 42192 |  | [National Map] Spike - Determine the ability to see multiple line strings on a segment. | To Do | NSSP-5892 | [National Map] Display Additional Layers | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-5789 | 42082 |  | [National Map] Develop the "Add Layer" UI Component for NatMap side drawer | To Do | NSSP-5892 | [National Map] Display Additional Layers | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Story | NSSP-5583 | 41459 |  | [National Map] Determine viability of design for viewing multiple layers simultaneously | To Do | NSSP-5892 | [National Map] Display Additional Layers | 3 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Story | NSSP-6224 | 43255 |  | [National Map]Applying Design System Side Drawer & Layer Panel - Right | To Do | NSSP-5997 | [National Map] Layers Panel Refactoring/Enhancements - Right side | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Story | NSSP-5804 | 42100 |  | [National Map] Add "Add Layer" UI Component to NatMap side drawer | To Do | NSSP-5997 | [National Map] Layers Panel Refactoring/Enhancements - Right side | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-5572 | 41429 |  | [National Map] Legend for Point Symbols | Done | NSSP-5997 | [National Map] Layers Panel Refactoring/Enhancements - Right side | 2 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-5570 | 41427 |  | [National Map] Add symbols for different network feature types | To Do | NSSP-5997 | [National Map] Layers Panel Refactoring/Enhancements - Right side | 5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-3140 | 36201 |  | [National Map] Independent Network search/selector component | To Do | NSSP-5997 | [National Map] Layers Panel Refactoring/Enhancements - Right side | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Story | NSSP-6025 | 42769 |  | [National Map] Display the "Current as of ?? AEST" Timestamp for network Layers | In Progress | NSSP-6000 | [National Map] Map and Networks timestamp updates | 5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Story | NSSP-6024 | 42768 |  | [National Map] Display OSM Data Timestamp on viewed map | Done | NSSP-6000 | [National Map] Map and Networks timestamp updates | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Story | NSSP-5164 | 40499 |  | [NatMap & Network Management] Expose dates of when "Road network data" was last updated | To Do | NSSP-6000 | [National Map] Map and Networks timestamp updates | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Test | NSSP-6262 | 43313 |  | build APIs for category and vehicle selection to performance case | Done | NSSP-6003 | [National Map] NatMap System Performance | 3.5
Test | NSSP-6201 | 43207 |  | [NatMap Performance] Prepare performance testing tool and env | Done | NSSP-6003 | [National Map] NatMap System Performance | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-6194 | 43188 |  | [NatMap Performance] Azure Monitoring | To Do | NSSP-6003 | [National Map] NatMap System Performance | 5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-6193 | 43187 |  | [NatMap Performance] Client side caching of NatMap tiles | In Progress | NSSP-6003 | [National Map] NatMap System Performance | 3 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-6192 | 43186 |  | [NatMap Performance] Schedule NatMap layer Truncate and Seed operations nightly | To Do | NSSP-6003 | [National Map] NatMap System Performance | 5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-6191 | 43185 |  | [NatMap Performance] Configure NatMap GeoServer layers | Done | NSSP-6003 | [National Map] NatMap System Performance | 5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-6190 | 43184 |  | [NatMap Performance] Configure a read replica DB specifically for NatMap | To Do | NSSP-6003 | [National Map] NatMap System Performance | 5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-6189 | 43183 |  | [NatMap Performance] Store map tiles in an efficient and scalable way, using Azure Blob Store | To Do | NSSP-6003 | [National Map] NatMap System Performance | 8 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-6187 | 43169 |  | de-masking is not fully applied to area | To Do | NSSP-6003 | [National Map] NatMap System Performance | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-6172 | 43119 |  | [NatMap] OpenLayer performance considerations | In Progress | NSSP-6003 | [National Map] NatMap System Performance | 5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Enabler | NSSP-6007 | 42745 |  | [NatMap] SPIKE: Layer and Tile Server Solution Architecture | Done | NSSP-6003 | [National Map] NatMap System Performance | 5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-6308 | 43466 |  | [NatMap] Adjust Pan/Select tool to expose ETL network data. | To Do | NSSP-6026 | [National Map] Road Selection Tool for NatMap | 8 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Bug | NSSP-6073 | 42901 |  | [Network Management] de-select all not work for segments after status change | Done | NSSP-6026 | [National Map] Road Selection Tool for NatMap | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-6072 | 42891 |  | [Network Management] Auto de-selection should happen after change segment | To Do | NSSP-6026 | [National Map] Road Selection Tool for NatMap | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-6284 | 43393 |  | Zoom to the bounds of the selected network | To Do | NSSP-5891 | [National Map] Save and Retrieve My Network Views | 5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-6283 | 43392 |  | Pass vehicle config component ID to display images | In Progress | NSSP-5891 | [National Map] Save and Retrieve My Network Views | 1 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-6155 | 43068 |  | [National Map] Delete a saved network view | Done | NSSP-5891 | [National Map] Save and Retrieve My Network Views | 2 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-6154 | 43066 |  | [National Map] Save/retrieve my network views | Done | NSSP-5891 | [National Map] Save and Retrieve My Network Views | 5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-5579 | 41451 |  | [National Map] Store recently viewed networks | Done | NSSP-5891 | [National Map] Save and Retrieve My Network Views | 3 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Story | NSSP-5571 | 41428 |  | [National Map] Add Share URL Button to NatMap UI | Done | NSSP-5891 | [National Map] Save and Retrieve My Network Views | 2 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-5955 | 42564 |  | [NatMap Splash] Present NatMap Splash to users when entering NatMap resource | Done | NSSP-6001 | [National Map] Splash Screens and Legal Requirements | 3 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-5868 | 42306 |  | [NatMap Splash] Investigate and design a consolidated splash screen to meet legal requirements. | Done | NSSP-6001 | [National Map] Splash Screens and Legal Requirements | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Task | NSSP-5840 | 42216 |  | [National Map] Generic Splash Screen | Done | NSSP-6001 | [National Map] Splash Screens and Legal Requirements | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Task | NSSP-6280 | 43384 |  | [NatMap] We need a public (no jwt token required) network find API | Done | NSSP-6071 | [National Map] Steel Thread - Type 1 Road Train Network - Spatial | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Task | NSSP-6279 | 43382 |  | [NatMap] Update QA data to point to correct/meaningful networks | Done | NSSP-6071 | [National Map] Steel Thread - Type 1 Road Train Network - Spatial | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Task | NSSP-6265 | 43320 |  | [Network Management: Audit/Legal]: Verify that we record sufficient audit/history data for Networks and NURs | To Do | NSSP-6071 | [National Map] Steel Thread - Type 1 Road Train Network - Spatial | 3 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-6136 | 43011 |  | [National Map] GeoServer Vector Tiles Type 1 Road Train (36.5m) Networks | Done | NSSP-6071 | [National Map] Steel Thread - Type 1 Road Train Network - Spatial | 0 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-5763 | 42051 |  | [Update Requests] Use of Conditions Library and how data is stored against the road segment. | Done | NSSP-1764 | Network Builder / NUR / NatMap - Support for Conditions / Restrictions | 8 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Task | NSSP-5704 | 41847 |  | [National Map & Update Requests] Side drawer UI refactor + Conditions/Restrictions/Approvals | Done | NSSP-1764 | Network Builder / NUR / NatMap - Support for Conditions / Restrictions | 3 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-3702 | 37372 |  | [Access Management] Update "Spatial" global menu design and menu options | Done | NSSP-1764 | Network Builder / NUR / NatMap - Support for Conditions / Restrictions | 0 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-3535 | 37017 |  | [Network Management] 'Networks' landing-page | Done | NSSP-1764 | Network Builder / NUR / NatMap - Support for Conditions / Restrictions | 8 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-3534 | 37013 |  | [Network Management] 'Create new network' - Support multiple network types | Done | NSSP-1764 | Network Builder / NUR / NatMap - Support for Conditions / Restrictions | 3 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-3065 | 35969 |  | [Network Management] Add Condition to Multiple Road Segments | Done | NSSP-1764 | Network Builder / NUR / NatMap - Support for Conditions / Restrictions | 5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-2406 | 34437 |  | [Network Management] Specify Condition (access_description) | Done | NSSP-1764 | Network Builder / NUR / NatMap - Support for Conditions / Restrictions | 2 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-1413 | 32304 |  | [Network Management] Networks - View Conditions/Restrictions outside of edit. | Done | NSSP-1764 | Network Builder / NUR / NatMap - Support for Conditions / Restrictions | 3 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-6074 | 42902 |  | [Annotations] Add click events to display network feature details | In Progress | NSSP-5315 | [Network Management] Spatial - Network Features | 3 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-5827 | 42161 |  | [Annotations] Finalise annotations UI | To Do | NSSP-5315 | [Network Management] Spatial - Network Features | 3 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-5826 | 42160 |  | [Annotations] Show Way2Go area features (aka annotations) in network maps | Done | NSSP-5315 | [Network Management] Spatial - Network Features | 3 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Enabler | NSSP-5694 | 41824 |  | Spike - Investigate the use of Network Annotation Points in OpenStreetMap (OSM) - Use of OSM Segments vs. Additional Points for Annotations | Done | NSSP-5315 | [Network Management] Spatial - Network Features | 3 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-3363 | 36700 |  | VicRoads Disruptions - Expose new fields & extract using pagination | Done | NSSP-5315 | [Network Management] Spatial - Network Features | 1 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-1143 | 10201 |  | Manage itinerary items within a network. | Done | NSSP-5315 | [Network Management] Spatial - Network Features | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-1136 | 10510 |  | Provide Tools to add, edit, or remove Network Annotations | Done | NSSP-5315 | [Network Management] Spatial - Network Features | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-1030 | 10252 |  | [Annotations] Show Way2Go point features (aka annotations) in network maps | Done | NSSP-5315 | [Network Management] Spatial - Network Features | 8 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-6309 | 43472 |  | Update Requests] FINAL - Amend wording advisory when viewing road segment selection | To Do | NSSP-6035 | [NUR/Builder/National Map] Enhance display and edit of selected Conditions/Restrictions - NHVR NatMap Road Selection Panel | 2 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Story | NSSP-6307 | 43462 |  | [Update Request] Allow multiple segments to use the conditions library | To Do | NSSP-6035 | [NUR/Builder/National Map] Enhance display and edit of selected Conditions/Restrictions - NHVR NatMap Road Selection Panel | 5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-6306 | 43461 |  | Fix condition action buttons on segment drawer | To Do | NSSP-6035 | [NUR/Builder/National Map] Enhance display and edit of selected Conditions/Restrictions - NHVR NatMap Road Selection Panel | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-6148 | 43047 |  | Handle conditions and restrictions when publishing an NUR | Done | NSSP-6035 | [NUR/Builder/National Map] Enhance display and edit of selected Conditions/Restrictions - NHVR NatMap Road Selection Panel | 1 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-5703 | 41846 |  | [Update Requests] Notification - Editing existing Condition or Restriction Pop-Up | Done | NSSP-6035 | [NUR/Builder/National Map] Enhance display and edit of selected Conditions/Restrictions - NHVR NatMap Road Selection Panel | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-5702 | 41845 |  | View segment conditions/restrictions in NURs, Published Networks, and NatMap | To Do | NSSP-6035 | [NUR/Builder/National Map] Enhance display and edit of selected Conditions/Restrictions - NHVR NatMap Road Selection Panel | 5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-5569 | 41426 |  | [Update Requests] Amend wording advisory when viewing road segment selection | In Progress | NSSP-6035 | [NUR/Builder/National Map] Enhance display and edit of selected Conditions/Restrictions - NHVR NatMap Road Selection Panel | 2 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-2237 | 34059 |  | [Update Requests] Adapt condition library component for use on maps (Single Condition). | Done | NSSP-6035 | [NUR/Builder/National Map] Enhance display and edit of selected Conditions/Restrictions - NHVR NatMap Road Selection Panel | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-6282 | 43391 |  | [Road Management] Proposals being created by some automated process? | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-6186 | 43165 |  | [Road Management] URL with passed segment IDs no longer shows segments | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-5648 | 41687 |  | Bug: Some RM's not in the rollout due to incorrect RM codes | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-5403 | 40995 |  | [Road Management] Correct background fill on dual/multiple road ownership notification tooltip | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Task | NSSP-5155 | 40450 |  | Road Management: Add more accounts to the rollout | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Bug | NSSP-4913 | 39847 |  | [Spatial-NW]when navigate back into 'Networks' table, the scrolling bar of page is missing it cause cannot paging | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Bug | NSSP-4902 | 39828 |  | Filter retired HVN segments from vw_heavy_vehicle_networks_minimal | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Bug | NSSP-4837 | 39450 |  | Gladstone Port is not available on the drop down list despite being a road manager | To Do | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-4836 | 39449 |  | Select segments along route no longer sorts segments into order | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Bug | NSSP-4636 | 38739 |  | [Spatial-RM] the notification not reflect correct when switch RM account | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Task | NSSP-4635 | 38736 |  | Routing: Collect request parameters and user id for any routes that take longer than x minutes | Done | NSSP-2402 | Road Management Production Support | 2 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Task | NSSP-4428 | 38518 |  | Road Ownership – Victoria – Maroondah City Council | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Bug | NSSP-4317 | 38399 |  | The network change set 'Updates' tab is showing retired segments | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Bug | NSSP-4064 | 38038 |  | Select segments within route doesn't clear previous selection | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Task | NSSP-4052 | 38026 |  | Add new RM's to the RM rollout | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY23Q3
Task | NSSP-3980 | 37857 |  | QA - Ports and Airports AoR Data in OSM | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Task | NSSP-3957 | 37812 |  | Add more Road Managers to the rollout | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Task | NSSP-3751 | 37425 |  | Address Victorian DELWP (FOR111) AoR Data in OSM | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Task | NSSP-3631 | 37262 |  | Update URL in Road Management Emails (/spatial to /access) | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Bug | NSSP-3533 | 37012 |  | [Spatial] Issues when using map tools combined with address search bar | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Bug | NSSP-3512 | 36991 |  | [Spatial-RM] open road management request drawer with blank after update a segment | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Task | NSSP-3497 | 36974 |  | Add some NSW Road Managers to the rollout | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Task | NSSP-3425 | 36853 |  | Add more SA RM's to the rollout | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Bug | NSSP-3373 | 36712 |  | [Spatial-NW] after save draft of a layer edit, the 'Save draft' button should be disabled until there is another change | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-3306 | 36578 |  | [Spatial-RM] Remove 7 Day Deletion Rule for Road Transfer Requests | Done | NSSP-2402 | Road Management Production Support | 1 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Task | NSSP-3251 | 36381 |  | [RM] Add more RM's to the rollout | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Task | NSSP-3136 | 36197 |  | [RM] Add Orange City Council to RM rollout (and comment out the spatial user code so that it can go to prod) | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Task | NSSP-3047 | 35942 |  | Road Management Rollout Support: The frontend should obtain the road managers from the backend via an API | Done | NSSP-2402 | Road Management Production Support | 1 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Bug | NSSP-2942 | 35686 |  | [Spatial-RM] Road Transfer Request Table issue when regulator user switch accounts | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-2932 | 35658 |  | [Spatial-RM] Send road management partner account emails to a designated 'spatial' address | Done | NSSP-2402 | Road Management Production Support | 3 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Bug | NSSP-2677 | 35045 |  | Road Names not found using Search function | To Do | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Task | NSSP-2663 | 35028 |  | Investigate what it would take to support transferring unmanaged segments to another road manager | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Bug | NSSP-2594 | 34837 |  | Selection Behaviour of Under Construction Roads in Road Management | To Do | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-2450 | 34516 |  | [Road Management] proposed segment drawer combined with selected segment drawer | To Do | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Task | NSSP-2319 | 34266 |  | Address Ports and Airports AoR Data in OSM | Done | NSSP-2402 | Road Management Production Support | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-5173 | 40517 |  | [Access Management] Roads Menu - Add "Health" Tab | To Do | NSSP-1743 | [Road Management] Refactoring Road Management and Implementing Workflow Side Strip | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-5095 | 40322 |  | [Road Management] Boundaries Layer - Layer names and tooltip | Done | NSSP-1743 | [Road Management] Refactoring Road Management and Implementing Workflow Side Strip | 1 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-3536 | 37018 |  | [Road Management] RTR - Backend API to support Attachments | To Do | NSSP-1743 | [Road Management] Refactoring Road Management and Implementing Workflow Side Strip | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-1915 | 33437 |  | Interrogate Road Ownership Changes for a Road Segment | To Do | NSSP-1743 | [Road Management] Refactoring Road Management and Implementing Workflow Side Strip | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Story | NSSP-361 | 10239 |  | Road Management: Define/update multiple managers for a single road segment or group of segments | To Do | NSSP-1277 | [Road Management] Support for multiple road ownership scenarios | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-6269 | 43330 |  | Context menu options are incorrect for NUR - intermittent | In Progress | NSSP-5954 | Spatial - Tech Debt - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Bug | NSSP-6258 | 43305 |  | [Production Issue]: Large Network or NUR not saving in production | To Do | NSSP-5954 | Spatial - Tech Debt - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Task | NSSP-6188 | 43177 |  | Tech Debt: Remove obsolete tables from the DB | To Do | NSSP-5954 | Spatial - Tech Debt - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Enabler | NSSP-6183 | 43155 |  | Tech Debt: Create a minimal developer-friendly Spatial/Postgres DB setup | To Do | NSSP-5954 | Spatial - Tech Debt - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Bug | NSSP-6173 | 43143 |  | [National Map & NUR] Network layer not persisting during user zoom events | Done | NSSP-5954 | Spatial - Tech Debt - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Bug | NSSP-6075 | 42903 |  | [Network Builder & NUR] "Select All Roads" timing out - White screen of death appears | Done | NSSP-5954 | Spatial - Tech Debt - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Bug | NSSP-6004 | 42739 |  | [Network Management]filter on search network datagrid table will existing displaying on the national map | Done | NSSP-5954 | Spatial - Tech Debt - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-5999 | 42724 |  | [Network Management] The Published networks view needs to filter out hidden networks | Done | NSSP-5954 | Spatial - Tech Debt - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-5963 | 42592 |  | [Network Management]Failed to submit NUR if not save draft first | Done | NSSP-5954 | Spatial - Tech Debt - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-5958 | 42586 |  | [Network Management] Layer tooltips overlay the checkbox which make checkbox not tickable | Done | NSSP-5954 | Spatial - Tech Debt - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-5956 | 42573 |  | [Network Management] daily regression fix | Done | NSSP-5954 | Spatial - Tech Debt - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-5864 | 42293 |  | Vehicle networks linking broken | Done | NSSP-5954 | Spatial - Tech Debt - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-5814 | 42127 |  | Select visible segments on road is not selecting additional segments | Done | NSSP-5954 | Spatial - Tech Debt - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Task | NSSP-5405 | 40999 |  | TECH DEBT - Unit Test Coverage for Map Service Layer (client-api-auth) | To Do | NSSP-5954 | Spatial - Tech Debt - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Bug | NSSP-4950 | 39901 |  | ArcGIS Online Classic web apps are being deprecated - SOON!! | To Do | NSSP-5954 | Spatial - Tech Debt - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q3
Story | NSSP-4360 | 38449 |  | [Network Management] All URL's need to work in the current Production portal frontend | To Do | NSSP-5954 | Spatial - Tech Debt - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Task | NSSP-2869 | 35527 |  | [SPATIAL] TECH DEBT - Move (TypeScript) types into common module/repo out of the UI | To Do | NSSP-5954 | Spatial - Tech Debt - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q3
Bug | NSSP-2260 | 34104 |  | Routing Performance: Performance degrades as the size of heavy_vehicle_network_road_segments grows | To Do | NSSP-5954 | Spatial - Tech Debt - FY24Q2 | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-6147 | 43042 |  | [Analytics] Organise Access - Add Google tags/events to track map usage | Done | NSSP-6145 | [Spatial] Tracking and Analytics | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Task | NSSP-6146 | 43041 |  | Determine what events we want to track with Google Tag Manager/GA | Done | NSSP-6145 | [Spatial] Tracking and Analytics | 1 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Enabler | NSSP-6199 | 43194 |  | [National Map Infra] Automate the deployment of the ETL function app (or alternative) | To Do | NSSP-5498 | Tech Enablement: Automate the provision of non-NHVR data sources for National Map | 5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Enabler | NSSP-6198 | 43193 |  | [National Map Infra] Setup the ETL logic to run on a schedule | To Do | NSSP-5498 | Tech Enablement: Automate the provision of non-NHVR data sources for National Map | 3 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Enabler | NSSP-6197 | 43192 |  | [National Map Infra] Create function app (or alternative) to run the ETL code | To Do | NSSP-5498 | Tech Enablement: Automate the provision of non-NHVR data sources for National Map | 1 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Enabler | NSSP-6196 | 43191 |  | [OBSOLETE] [National Map Infra] Schema to store the ETL'd networks | Done | NSSP-5498 | Tech Enablement: Automate the provision of non-NHVR data sources for National Map | 0 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Task | NSSP-6044 | 42813 |  | [National Map] ETL Service - Performance Analysis | To Do | NSSP-5498 | Tech Enablement: Automate the provision of non-NHVR data sources for National Map | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Task | NSSP-6043 | 42812 |  | [National Map] ETL Service - Error Handling | To Do | NSSP-5498 | Tech Enablement: Automate the provision of non-NHVR data sources for National Map | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Task | NSSP-6042 | 42811 |  | [National Map] ETL Service - Scalability Test | To Do | NSSP-5498 | Tech Enablement: Automate the provision of non-NHVR data sources for National Map | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Task | NSSP-6041 | 42810 |  | [National Map] ETL Service - Data Consistency | To Do | NSSP-5498 | Tech Enablement: Automate the provision of non-NHVR data sources for National Map | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Task | NSSP-6040 | 42809 |  | [National Map] ETL Service - Prototype Integration | To Do | NSSP-5498 | Tech Enablement: Automate the provision of non-NHVR data sources for National Map | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Task | NSSP-6039 | 42807 |  | [National Map] ETL Service - Compatibility Check | To Do | NSSP-5498 | Tech Enablement: Automate the provision of non-NHVR data sources for National Map | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Story | NSSP-5758 | 42031 |  | [National Map] Spike - Determine automation options for NatMap to consume non-NHVR data | Done | NSSP-5498 | Tech Enablement: Automate the provision of non-NHVR data sources for National Map | 5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-5654 | 41693 |  | NSW- Automate load of data onto NHVR system (GeoStore) | To Do | NSSP-5498 | Tech Enablement: Automate the provision of non-NHVR data sources for National Map | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Story | NSSP-5653 | 41692 |  | VIC- Automate disruptions ETL (GeoStore) | To Do | NSSP-5498 | Tech Enablement: Automate the provision of non-NHVR data sources for National Map | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q1
Task | NSSP-702 | 10982 |  | [SPATIAL-Q4] Spike - Draft data model to accommodate structures data from various sources. | Done | NSSP-321 | Visualise Asset structures within layers on NHVR Maps | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Task | NSSP-518 | 10976 |  | [Spatial Q2/3] - Asset detail view | To Do | NSSP-321 | Visualise Asset structures within layers on NHVR Maps | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-10 | CX-Design
Story | NSSP-373 | 10467 |  | [SPATIAL] Layers: Add structural restriction information - Restricted Bridges, Height Clearance, Level-crossings. | Done | NSSP-321 | Visualise Asset structures within layers on NHVR Maps | 0 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial
Enabler | NSSP-363 | 10461 |  | [Network Builder] HV Restricted Structures & NHVR Maps Relationships | To Do | NSSP-321 | Visualise Asset structures within layers on NHVR Maps | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial | FY24Q2
Sub-task | NSSP-3614 | 37230 | 38135 | Plan for OpenData in the Backlog / Horizon Planning | Done |  |  | 3.5 | 4b3f5476-4a14-4b53-836f-f33f51dee39a-3 | NSP-Spatial